## Sheet1
Time | Responsable | Activity
2017-03-30 | me | Finish Software Architecture document
2017-03-31
2017-04-01
2017-04-02 | me | Make all functions to call API.
2017-04-03 | me | Interpret all data of each function to API
2017-04-04 | me | Give weighted average for each setting. (Make formula)
2017-04-05
2017-04-06
2017-04-07 | me | Create structure of project (Visual) Import libraries
2017-04-08
2017-04-09 | me | Define colors for application and import font-awesome (icons)
2017-04-10 | me | Make bars for each aspect
2017-04-11 | me | Create popup for house choosed
2017-04-12 | me | Desing text, size, font, etc
2017-04-13 | me | Merge all elements and create alfa app
2017-04-14 | me | Make test with differents cases
2017-04-15
2017-04-16 | me | Fix bug and review what more can be added
2017-04-17 | me | Release app and wait for judges opinion.